## Project Planner
Fake News Detection Tool Project Gantt Chart (Updated as of March 11, 2024)
| Select a period to highlight at right. A legend describing the charting follows. | [6 empty] | Period Highlight: | 10 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete
ACTIVITY # | ACTIVITY | Sub-Activity | Dependencies (Activity) | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Weeks
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Selection of Template |  |  | 1 | 2 | 1 | 2 | 100%
2 | Motivations |  |  | 1 | 2 | 1 | 2 | 100%
3 | Stakeholders Requirements Elicitation |  | 1,2 | 2 | 1 | 2 | 1 | 100%
4 | Literature Analysis |  | 1 | 2 | 2 | 2 | 2 | 100%
5 | Pitch Project |  | 1,2,3,4 | 4 | 2 | 4 | 2 | 100%
6 | Design |  | 5 | 6 | 3 | 6 | 3 | 100%
7 | Project Structure Dev |  | 6 | 6 | 3 | 6 | 3 | 100%
8 | Testing and Evaluation Plan definition |  | 7 | 6 | 3 | 6 | 3 | 100%
9 | Database Search |  |  | 7 | 1 | 7 | 1 | 100%
10 | Prototype Development | Prototyping 1- Low Level | 7 | 8 | 2 | 8 | 2 | 100%
11 | Preliminary Report |  | All of Above | 9 | 2 | 9 | 2 | 100%
12 | NLP Model Development | Data Preprocessing | 9 | 10 | 1 | 12 | 4 | 100%
13 |  | Feature Extraction | 12 | 10 | 1 | 16 | 4 | 100%
14 |  | Feature Selection | 13 | 11 | 1 | 16 | 3 | 100%
15 |  | Model Selection | 14 | 11 | 1 | 17 | 3 | 100%
16 |  | Model Training Classification | 15 | 11 | 1 | 17 | 3 | 100%
17 |  | Model Evaluation | 16 | 12 | 1 | 17 | 3 | 100%
18 |  | Hyper-parameter tunning/Cross Validation | 17 | 12 | 1 | 17 | 3 | 100%
19 |  | Flask Development |  | 13 | 2 | 13 | 7 | 100%
20 | Flask Deployment model deployment with user interface | Prototyping 2- Medium Level | 19 | 11 | 1 | 17 | 1 | 100%
21 |  | Model Testing and Evaluation 1(formative) | 20 | 12 | 1 | 17 | 3 | 100%
22 |  | Prototyping 3- High Level | 21 | 13 | 1 | 18 | 1 | 25%
23 |  | Testing and Evaluation -User Feedback (Formative) | 22 | 14 | 1 | 18 | 3 | 100%
24 | Error Handing |  | 23 | 15 | 2 | 19 | 2 | 100%
26 | Summative User Evaluation |  | All of Above | 15 | 1 | 19 | 1 | 100%
27 | Final Development Modifications |  | 25,26 | 16 | 2 | 20 | 2 | 100%
28 | Delivery/Deployment |  | 27 | 17 | 1 | 21 | 1 | 100%
29 | Final Report |  | All of Above | 18 | 2 | 20 | 4 | 50%